## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As an analyst, I want to upload a CSV containing transactions so that I can detect fraud. | MUST | Dataset | Vishwas | Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want the system to clean and preprocess transactions automatically. | MUST | US01 | Vishwas | Completed
Sprint 1 | Sprint 1 | US03 | As an analyst, I want to see fraud probabilities for each transaction. | MUST | Model Artifacts | Vishwas | Completed
Sprint 1 | Sprint 1 | US04 | As a manager, I want adjustable fraud threshold and review band. | SHOULD | US03 | Vishwas | Completed
Sprint 2 | Sprint 2 | US05 | As an analyst, I want visual dashboards (graphs/histograms). | SHOULD | US03 | Vishwas | Completed
Sprint 2 | Sprint 2 | US06 | As a user, I want explanations for why a transaction was flagged. | COULD | US03 | Vishwas | Completed
Sprint 2 | Sprint 2 | US07 | As an admin, I want login/authentication to secure the tool. | MUST | - | Vishwas | Completed
Sprint 2 | Sprint 2 | US08 | As an analyst, I want to download scored results. | MUST | US03 | Vishwas | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task End Date | Team Member | Activity | Status | Est. Hrs
US01 | T1.1 | Setup project structure & environment | 2025-11-10 | 2025-11-10 | Vishwas | Development | Completed | 3
US01 | T1.2 | Build CSV upload interface in Streamlit | 2025-11-10 | 2025-11-11 | Vishwas | Development | Completed | 4
US02 | T2.1 | Implement preprocessing & feature engineering | 2025-11-11 | 2025-11-12 | Vishwas | Development | Completed | 5
US03 | T3.1 | Integrate model artifacts & score transactions | 2025-11-12 | 2025-11-13 | Vishwas | Development | Completed | 5
US04 | T4.1 | Add fraud threshold + review band slider | 2025-11-13 | 2025-11-13 | Vishwas | Development | Completed | 2
US05 | T5.1 | Create probability distribution graphs (Plotly) | 2025-11-15 | 2025-11-15 | Vishwas | Development | Completed | 3
US06 | T6.1 | Add local LLM / fallback rule-based explainer | 2025-11-15 | 2025-11-16 | Vishwas | Development | Completed | 4
US07 | T7.1 | Add login/auth with streamlit-authenticator | 2025-11-16 | 2025-11-16 | Vishwas | Development | Completed | 2
US08 | T8.1 | Add download scored CSV button | 2025-11-17 | 2025-11-17 | Vishwas | Development | Completed | 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Model artifacts too large; system lagging | Shifted project to C-drive, cleaned RAM
Sprint 1 | Day 2 | Threshold tuning issue; all outputs showing FRAUD | Added suggested threshold, fixed preprocessing
Sprint 1 | Day 3 | Upload dataset mismatched columns | Implemented auto-normalization of column names
Sprint 2 | Day 1 | LLM explanation failing on some rows | Created fallback rule-based explainer
Sprint 2 | Day 2 | GitHub push failed due to large files | Ignored artifacts in .gitignore & uploaded manually

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-10 | 2025-11-13 | Vishwas | Breaking tasks into smaller pieces | Training large models locally | Writing clean modular code | Added auto-normalization & threshold tuning
2 | Sprint 2 | 2025-11-14 | 2025-11-17 | Vishwas | Using dashboards early | Keeping artifacts inside Git | Maintaining consistent preprocessing | Improved UI, added authentication